## 2014 draft schedule
Task | jan | feb | mar | april | may | jun | jul | aug | sep | oct | nov | dec
Pre-treatment monitoring (UofA) | bar: april to jun
Treatments (Caro's) | bar: jun to dec
Monitoring assistance (Forest Guild YCC) | bar: may to jun; sep
Socio-economic monitoring (Ecotone) | bar: may to jun
Outreach newsletter story (Sierra Club) | may: planning; aug: publication
Multi-party meetings | bar: feb to april

## 2014-2016 sub-contracts
Year
Partner | 2014 | 2015 | 2016
Caro's | x | x | x
Forest Guild (O. Romero) | x | x | x
NE Constr. |  | x
Sierra Club | xa | xb | xa
Ecotone | x | x | x
a Mileage reimburse
b Meeting space and supplies